# بسم الله الرحمن الرحيم

# Yoka Store — Detailed Sub-Tasks for Each Member

## Integrated Sales & Warehouse Management (SWM) + E-Commerce Platform (ECP)

Full-Stack Sequential Relay Model — Timeline: September 25, 2026 to October 01, 2026

# 1. Executive Summary & Team Allocation

Each developer operates as a Full-Stack Engineer responsible for delivering their entire bulk package end-to-end (Database schema, Backend APIs, Frontend UI, Activity Log instrumentation, and verification) before handing off to the next engineer.┌────────────────────────────────────────────────────────────────────────────────────────────────────────┐

│                                       SEQUENTIAL RELAY TIMELINE                                        │

├────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ [Sep 25, 08:00 AM - Sep 26, 02:00 PM] ──► Moustafa Maher  : Bulk 1 (Infra, DB, Auth & Master Data)    │

│ [Sep 26, 02:30 PM - Sep 27, 11:00 PM] ──► Yassen Ahmed    : Bulk 2 (Purchasing, Stock & POS Terminal)  │

│ [Sep 28, 08:00 AM - Sep 29, 02:00 PM] ──► Adel Ahmed      : Bulk 3 (Storefront, Sync & Checkout)       │

│ [Sep 29, 02:30 PM - Sep 30, 11:00 PM] ──► Boda Essam      : Bulk 4 (Portal, Logs UI, Reports & Crons)  │

│ [Oct 01, 08:00 AM - Oct 01, 08:00 PM] ──► ALL 4 MEMBERS   : Joint Day 7 (Stress Tests & Go-Live)       │

└────────────────────────────────────────────────────────────────────────────────────────────────────────┘

# 2. Member 1: Moustafa Maher (Project Lead & Full-Stack Architect)

## Assigned Scope: Bulk 1 — Infrastructure, Core Database, Shared Engine, Auth & Master Data

Window: Sep 25, 2026 (08:00 AM) to Sep 26, 2026 (02:00 PM)
Total Allocated Hours: 30 Hours
Handoff Target: Yassen Ahmed at Sep 26, 2026 (02:00 PM)

### Sub-Task MM-1.1: Hostinger VPS Provisioning & System Hardening

- Domain: DevOps & Infrastructure

- Time Estimate: 4 Hours (Sep 25, 08:00 AM – 12:00 PM)

- Dependencies: Hostinger VPS root access credentials.

- Detailed Execution Steps:

  - SSH into Hostinger Ubuntu 24.04 LTS server with ED25519 key; disable root password login.

  - Update packages (apt update && apt upgrade -y).

  - Configure UFW firewall: allow ports 22 (SSH), 80 (HTTP), 443 (HTTPS); deny all other incoming traffic.

  - Install Node.js v20 LTS via NodeSource repository; install global tools: pm2, pnpm, typescript.

  - Install MySQL 8.0 Server; run mysql_secure_installation; tune my.cnf:

    - max_connections = 300

    - innodb_buffer_pool_size = 4G

    - innodb_log_file_size = 512M

    - innodb_flush_log_at_trx_commit = 2

  - Install Redis Server 7.2; configure redis.conf:

    - Set strong requirepass

    - maxmemory 1gb

    - maxmemory-policy volatile-lru

  - Install and configure Nginx web server; enable gzip and basic rate-limiting configurations.

- Deliverables: Operational Ubuntu 24.04 VPS with hardened MySQL, secured Redis, Node.js 20, PM2, and Nginx.

- Acceptance Criteria: systemctl status mysql, systemctl status redis-server, and systemctl status nginx all return active (running).

### Sub-Task MM-1.2: Complete Database Schema Migration (35+ Tables) & Seeding

- Domain: Database Engineering

- Time Estimate: 8 Hours (Sep 25, 12:30 PM – 08:30 PM)

- Dependencies: MM-1.1 completed.

- Detailed Execution Steps:

  - Create database yoka_store_db with utf8mb4 character set and utf8mb4_unicode_ci collation.

  - Write structured SQL migration files for all 35+ tables defined in the Technical Plan:

    - Core & Org: branches, users, categories, brands, products, product_variants, inventory_balances, inventory_movements.

    - SWM Purchasing & Stock: suppliers, purchase_invoices, purchase_invoice_items, supplier_payments, inventory_counts.

    - SWM POS & Sales: swm_customers, cash_registers, cash_register_sessions, cash_transactions, swm_sales_invoices, swm_sales_invoice_items, expenses.

    - E-Commerce (ECP): ecp_customers, ecp_addresses, ecp_carts, ecp_cart_items, ecp_orders, ecp_order_items, ecp_payments, ecp_coupons, ecp_reviews, ecp_shipping_zones.

    - System & Logs: sync_events, audit_logs, activity_logs, alert_events.

  - Create composite indexes, foreign key constraints with ON DELETE RESTRICT for financial integrity.

  - Build automated seeder script seed.js:

    - Default Main Branch ("الفرع الرئيسي")

    - Super Admin user (admin@yokastore.com) with bcrypt-hashed password (salt rounds = 12)

    - Base product categories and attribute sets (Sizes: S, M, L, XL, XXL; Colors: Black, White, Navy).

- Deliverables: migrations/001_initial_schema.sql and seeders/seed.js executed cleanly.

- Acceptance Criteria: SHOW TABLES; shows 35+ tables; foreign keys enforce referential integrity without errors.

### Sub-Task MM-1.3: Monorepo Setup, Shared Database/Redis Connectors & Activity Log Engine

- Domain: Core Backend Infrastructure

- Time Estimate: 5 Hours (Sep 25, 09:00 PM – Sep 26, 02:00 AM)

- Dependencies: MM-1.2 completed.

- Detailed Execution Steps:

  - Initialize Git repository with branches main, staging, and strict PR conventions.

  - Implement server/shared/db.js using mysql2/promise connection pool (connectionLimit: 50, waitForConnections: true).

  - Implement server/shared/redis.js using ioredis with auto-reconnect strategy and event listeners.

  - Implement the Central Activity Logger server/shared/activityLogger.js:async function logActivity({ userId, branchId, actionType, entityType, entityId, oldValue, newValue, ipAddress, userAgent, notes })

    - Handles serializing JSON snapshots of oldValue and newValue.

    - Asynchronous fire-and-forget query to activity_logs table preventing performance degradation.

  - Implement authMiddleware.js for JWT verification and RBAC permission checks (requireRole(['admin', 'manager'])).

- Deliverables: Shared utility module exportable to all subsequent backend routes.

- Acceptance Criteria: Calling logActivity() writes an accurate row to activity_logs with JSON diffs within < 5ms.

### Sub-Task MM-1.4: Master Data Backend APIs (Users, Branches, Categories, Products & Variants)

- Domain: Backend API Development

- Time Estimate: 6 Hours (Sep 26, 08:00 AM – 02:00 PM)

- Dependencies: MM-1.3 completed.

- Detailed Execution Steps:

  - Build Auth API endpoints:

    - POST /api/auth/login (generates access token 1h + refresh token 7d in Redis)

    - POST /api/auth/refresh

    - POST /api/auth/logout

  - Build Branch & User Management APIs:

    - GET /api/swm/branches, POST /api/swm/branches, PUT /api/swm/branches/:id

    - GET /api/swm/users, POST /api/swm/users, PUT /api/swm/users/:id/role

  - Build Product Catalog & Variant APIs:

    - POST /api/swm/products (creates parent product + variants in a single transaction)

    - GET /api/swm/products (with branch inventory balance joins, pagination, and barcode search)

    - PUT /api/swm/products/:id (captures old vs new price, logs activity)

  - Instrument all write operations with logActivity().

- Deliverables: Tested REST endpoints documented with sample requests/responses.

- Acceptance Criteria: All endpoints return standard { success: true, data: ... } format; 100% of mutations write to activity_logs.

### Sub-Task MM-1.5: Master Data Admin UI & Authentication Screens (Full-Stack Component)

- Domain: Frontend Web Development (React + Vite SPA)

- Time Estimate: 7 Hours (Spread over Sep 25-26, finished by Sep 26, 02:00 PM)

- Dependencies: MM-1.4 endpoints ready.

- Detailed Execution Steps:

  - Scaffold React + Vite application under client-swm/; configure Axios interceptors for JWT auto-refresh.

  - Build Login Screen with responsive layout and error handling.

  - Build User & Branch Management views with modal forms for creating and editing staff accounts.

  - Build Product Catalog Management UI:

    - Product creation modal with dynamic variant generator (Matrix: Size x Color).

    - SKU and Barcode auto-generation.

    - Table listing with inline search, category filter, and branch balance indicators.

- Deliverables: Functional React dashboard with authentication and master data CRUD.

- Hand-off Checklist to Yassen Ahmed:

  - Hostinger VPS accessible via Git and SSH.

  - MySQL database migrated with all 35+ tables and seeded admin user.

  - Shared db.js, redis.js, and logActivity() available in repository.

  - Products and variants can be created and viewed in UI and DB.

# 3. Member 2: Yassen Ahmed (Full-Stack Engineer)

## Assigned Scope: Bulk 2 — Purchasing, Suppliers, Inventory Balances & POS Cashier Terminal

Window: Sep 26, 2026 (02:30 PM) to Sep 27, 2026 (11:00 PM)
Total Allocated Hours: 32 Hours
Handoff Target: Adel Ahmed at Sep 27, 2026 (11:00 PM)

### Sub-Task YA-2.1: Supplier Management & Purchase Invoices API (Backend)

- Domain: Backend API Development

- Time Estimate: 6 Hours (Sep 26, 02:30 PM – 08:30 PM)

- Dependencies: MM-1.4 (Product and variant tables ready).

- Detailed Execution Steps:

  - Build Supplier CRUD APIs:

    - GET /api/swm/suppliers, POST /api/swm/suppliers, PUT /api/swm/suppliers/:id

  - Build Purchase Invoices API (POST /api/swm/purchases):

    - Wrap invoice creation, item insertion, and inventory balance updates inside a strict db.beginTransaction().

    - Update or insert rows into inventory_balances (quantity_on_hand += item.quantity).

    - Recalculate Weighted Average Cost (WAC):
$$\text{New Cost} = \frac{(\text{Current Qty} \times \text{Current Cost}) + (\text{Incoming Qty} \times \text{Unit Cost})}{\text{Current Qty} + \text{Incoming Qty}}$$

    - Insert audit row into inventory_movements with movement_type = 'purchase'.

    - Record supplier ledger payment/balance.

  - Instrument every invoice creation in logActivity() recording supplier ID, total amount, and invoice number.

- Deliverables: Complete purchase processing API with automated stock & cost updates.

- Acceptance Criteria: Submitting a purchase invoice increases inventory_balances.quantity_on_hand and logs movement_type = 'purchase'.

### Sub-Task YA-2.2: Supplier & Purchase Invoices Frontend UI

- Domain: Frontend Web Development (React)

- Time Estimate: 5 Hours (Sep 26, 09:00 PM – Sep 27, 02:00 AM)

- Dependencies: YA-2.1 completed.

- Detailed Execution Steps:

  - Build Supplier Directory page with supplier balance cards and payment history modal.

  - Build "New Purchase Invoice" screen:

    - Searchable product variant selector.

    - Dynamic row addition with quantity, unit cost, discount, and calculated line totals.

    - Destination branch selector.

    - Immediate validation preventing negative quantities or zero costs.

  - Build Purchase Invoices history log with status badges (received, pending, partial).

- Deliverables: Integrated purchase workflow screens in client-swm/.

- Acceptance Criteria: User creates a purchase invoice on UI; stock balance is immediately updated in the database.

### Sub-Task YA-2.3: POS Terminal Fast Sale Engine & Cash Drawer Sessions API (Backend)

- Domain: Backend API & Financial Transactions

- Time Estimate: 8 Hours (Sep 27, 08:00 AM – 04:00 PM)

- Dependencies: YA-2.1 (Inventory balances populated).

- Detailed Execution Steps:

  - Cash Register Sessions API:

    - POST /api/swm/pos/session/open: Opens cashier drawer with opening cash balance (opening_balance).

    - POST /api/swm/pos/session/close: Closes session with expected vs actual cash audit, logs variance.

    - POST /api/swm/pos/cash-transaction: Cash in / Cash out (petty cash expense).

  - High-Speed POS Sale Transaction API (POST /api/swm/pos/sale):

    - Uses db.beginTransaction() and SELECT ... FOR UPDATE row-level locks on inventory_balances.

    - Validates available stock; rejects transaction if quantity_on_hand < requested_qty.

    - Deducts inventory balance and records row in inventory_movements (movement_type = 'sale').

    - Generates sequential invoice number: INV-BR{branch_id}-{YYYYMMDD}-{XXXX}.

    - Inserts invoice record into swm_sales_invoices and items into swm_sales_invoice_items.

    - Updates cash drawer session total.

    - Calls logActivity() with cashier ID, invoice number, and payment method (cash, card, split).

- Deliverables: POS backend controller handling concurrent checkout requests safely.

- Acceptance Criteria: Prevents overselling with atomic transactions; rollbacks completely on insufficient stock error.

### Sub-Task YA-2.4: POS Fast Cashier Frontend UI & 80mm Thermal Receipt Printing

- Domain: Frontend Web Development (React POS UI)

- Time Estimate: 9 Hours (Sep 27, 04:00 PM – 10:30 PM)

- Dependencies: YA-2.3 completed.

- Detailed Execution Steps:

  - Build high-speed POS layout:

    - Barcode scanner input field with automatic item insertion on barcode scan.

    - Quick product grid with search and category tabs.

    - Size/Color selector popover for multi-variant items.

    - interactive cart table: change quantities with keyboard shortcuts (+, -, Delete).

  - Build Payment Modal:

    - Total, discount input, tax display, and tender calculation (Cash received vs Change due).

    - Multi-payment support (Cash + Credit Card).

  - Implement Thermal Receipt Printing (80mm CSS media query):

    - Store logo, invoice number, cashier name, date/time, itemized table, total, tax, barcode/QR code.

    - Auto-trigger window.print() upon sale confirmation.

  - Build Session Opening/Closing UI with cash reconciliation form.

- Deliverables: High-speed POS interface operational in client-swm/.

- Hand-off Checklist to Adel Ahmed:

  - Complete purchase cycle functioning (Supplier -> Invoice -> Stock increment).

  - POS Cashier Terminal operational with instant stock deduction.

  - Session cash control and thermal receipt printing working.

  - All sales and purchases recorded in inventory_movements and activity_logs.

# 4. Member 3: Adel Ahmed (Full-Stack Engineer)

## Assigned Scope: Bulk 3 — ECP Storefront, Sync Engine, Cart Reservation & Checkout

Window: Sep 28, 2026 (08:00 AM) to Sep 29, 2026 (02:00 PM)
Total Allocated Hours: 30 Hours
Handoff Target: Boda Essam at Sep 29, 2026 (02:00 PM)

### Sub-Task AA-3.1: Public Catalog & Cart APIs (Backend)

- Domain: Backend API Development

- Time Estimate: 6 Hours (Sep 28, 08:00 AM – 02:00 PM)

- Dependencies: Bulk 1 & Bulk 2 (Products and inventory populated).

- Detailed Execution Steps:

  - Build ECP Catalog APIs:

    - GET /api/ecp/catalog: Paginated public products with category/price/size filters, only querying variants with active inventory.

    - GET /api/ecp/catalog/:slug: Detailed product view with images, variants, size chart, and available stock.

    - Redis caching for product catalog (ttl: 300s) invalidated upon product updates.

  - Build Session/User Cart APIs (/api/ecp/cart):

    - Supports guest carts (via cookie UUID) and registered customer carts.

    - Add to cart, update quantity, remove item, sync cart on login.

    - Real-time stock validation against inventory_balances for the online store branch.

- Deliverables: High-performance public catalog and cart endpoints in server/routes/ecp/.

- Acceptance Criteria: Catalog queries respond in < 60ms with Redis cache enabled; out-of-stock variants cannot be added to cart.

### Sub-Task AA-3.2: ECP Storefront Web Application (Next.js 14 Frontend)

- Domain: Frontend Web Development (Next.js App Router)

- Time Estimate: 9 Hours (Sep 28, 02:30 PM – 11:30 PM)

- Dependencies: AA-3.1 completed.

- Detailed Execution Steps:

  - Scaffold Next.js 14 application under client-ecp/ with Tailwind CSS and responsive layout.

  - Build Homepage:

    - Hero banner, featured collections, new arrivals carousel.

  - Build Catalog & Filter Page:

    - Faceted sidebar filters (Categories, Size, Color, Price Range).

    - Sort options (Price: Low to High, Popularity, Newest).

  - Build Product Details Page (PDP):

    - Multi-image gallery with zoom preview.

    - Color and Size selector with instant out-of-stock visual indicators.

    - "Add to Cart" button with animated micro-interactions.

  - Build Slide-over Cart Drawer:

    - Real-time total calculation, free shipping threshold progress bar.

- Deliverables: Modern, mobile-first responsive e-commerce storefront in client-ecp/.

- Acceptance Criteria: Mobile responsiveness verified; Lighthouse Performance score > 90.

### Sub-Task AA-3.3: Temporary Inventory Reservation & BullMQ Sync Engine (Backend)

- Domain: Real-time Integration & Queue Processing

- Time Estimate: 7 Hours (Sep 29, 12:00 AM – 07:00 AM)

- Dependencies: AA-3.1 and YA-2.3 (POS inventory balances).

- Detailed Execution Steps:

  - Implement Temporary Cart Reservation (15-minute hold):

    - When customer proceeds to checkout, create a temporary reservation key in Redis:
SET ecp:reserve:{variant_id}:{cart_id} {qty} EX 900

    - Decrement available online inventory virtual counter.

    - BullMQ delayed job scheduled for 15 minutes to release hold if order not paid.

  - Implement Distributed Mutex Lock:

    - Prevent race conditions using Redis Lock pattern (SET lock:variant:{id} {uuid} NX EX 10).

  - Build Bi-directional Sync Worker:

    - BullMQ worker listening to SWM POS sales and ECP orders.

    - When POS sells an item in the branch designated for online fulfillment, trigger WebSocket/Redis PubSub event updating storefront stock display.

- Deliverables: Robust stock reservation and concurrency guard in server/jobs/syncWorker.js.

- Acceptance Criteria: Multiple users attempting to checkout the last available unit results in exactly one successful reservation; others receive "Item reserved by another shopper".

### Sub-Task AA-3.4: One-Page Checkout Flow & Payment Gateway Integration (Full-Stack)

- Domain: Full-Stack E-Commerce Checkout

- Time Estimate: 7 Hours (Sep 29, 07:30 AM – 01:30 PM)

- Dependencies: AA-3.2 and AA-3.3 completed.

- Detailed Execution Steps:

  - Build One-Page Checkout UI:

    - Shipping address form (Governorate dropdown with dynamic shipping cost calculation).

    - Delivery instructions and customer contact phone.

    - Payment method selector: Cash on Delivery (COD) vs Online Card Payment.

  - Implement Payment Gateways:

    - Integrate Stripe Elements / Paymob iFrame securely.

    - Backend endpoint POST /api/ecp/checkout/create-intent.

    - Secure Webhook endpoint POST /api/ecp/checkout/webhook to handle payment_intent.succeeded.

  - Implement Order Finalization inside db.beginTransaction():

    - Convert cart to ecp_orders and ecp_order_items.

    - Release Redis temporary reservation and commit permanent deduction in inventory_balances.

    - Trigger logActivity() for online order placement.

  - Build Order Confirmation Page with order tracking reference.

- Deliverables: Fully functioning checkout flow from cart to payment receipt.

- Hand-off Checklist to Boda Essam:

  - Live e-commerce store with catalog, search, and variant filtering.

  - Redis 15-minute temporary reservation active during checkout.

  - Stripe/Paymob payment and COD orders successfully write to ecp_orders.

  - Stock deductions sync smoothly between online purchases and warehouse balances.

# 5. Member 4: Boda Essam (Full-Stack Engineer)

## Assigned Scope: Bulk 4 — Customer Portal, Coupons, Activity Log Viewer, Reports & Automation

Window: Sep 29, 2026 (02:30 PM) to Sep 30, 2026 (11:00 PM)
Total Allocated Hours: 32 Hours
Handoff Target: Entire Team for Day 7 Joint Launch at Sep 30, 2026 (11:00 PM)

### Sub-Task BE-4.1: Customer Portal, Order Tracking & WhatsApp Notifications (Full-Stack)

- Domain: Full-Stack Customer Portal

- Time Estimate: 7 Hours (Sep 29, 02:30 PM – 09:30 PM)

- Dependencies: Bulk 3 (Orders and checkout operational).

- Detailed Execution Steps:

  - Backend Customer Account APIs (/api/ecp/customer/):

    - GET /api/ecp/customer/orders: List customer purchase history with shipping status.

    - GET /api/ecp/customer/orders/:id: Detailed invoice view.

    - PUT /api/ecp/customer/profile: Update address book and phone.

  - Customer Portal Frontend UI in client-ecp/:

    - Order history list with visual timeline stepper (Pending -> Confirmed -> Shipped -> Delivered).

    - Address management card grid.

  - WhatsApp Order Confirmation Integration:

    - Auto-generate formatted WhatsApp link with order ID, customer name, items summary, and total:
https://wa.me/{store_phone}?text={encoded_message}.

    - Place "Share / Track via WhatsApp" button on order confirmation screen.

- Deliverables: Self-service customer account portal and WhatsApp order alert generator.

- Acceptance Criteria: Customer logs in, views their historical orders with current status, and can launch pre-filled WhatsApp confirmation.

### Sub-Task BE-4.2: Coupons Engine, Promotions & Product Reviews (Full-Stack)

- Domain: Full-Stack Marketing Tools

- Time Estimate: 6 Hours (Sep 29, 10:00 PM – Sep 30, 04:00 AM)

- Dependencies: Bulk 3 & BE-4.1.

- Detailed Execution Steps:

  - Coupons Engine:

    - Table ecp_coupons handling: code, discount_type (percentage or fixed), discount_value, min_order_amount, max_discount, usage_limit, expires_at.

    - Backend verification API: POST /api/ecp/coupons/validate.

    - Frontend checkout integration: instant coupon code application with discount line display.

  - Admin Coupon Management:

    - SWM dashboard interface to create, activate, expire, and monitor coupon usages.

  - Product Reviews Component:

    - Customer review submission modal with 1-5 star rating and comment.

    - Admin approval status toggle (approved, pending).

- Deliverables: Dynamic coupon engine and product review system.

- Acceptance Criteria: Expired or below-minimum coupons rejected with descriptive error; valid coupon deducts correct amount on checkout.

### Sub-Task BE-4.3: Activity Log Explorer & Audit Trail UI (Full-Stack)

- Domain: Full-Stack Audit & Governance

- Time Estimate: 8 Hours (Sep 30, 08:00 AM – 04:00 PM)

- Dependencies: MM-1.3 (activity_logs data populated by all modules).

- Detailed Execution Steps:

  - Backend Activity Log Explorer API (GET /api/swm/activity-logs):

    - Server-side pagination, sorting, and multi-parameter filtering:

      - By User ID / Employee

      - By Branch ID

      - By Action Type (CREATE, UPDATE, DELETE, POS_SALE, LOGIN, PRICE_CHANGE, CASH_OUT)

      - By Date range (From date - To date)

    - GET /api/swm/activity-logs/:id: Retrieves full snapshot data.

  - Activity Log Explorer UI in client-swm/:

    - Clean data table with color-coded action badges (Green for Sales/Create, Yellow for Update, Red for Delete/Cash Out).

    - Filter toolbar with instant search.

    - Interactive Diff Modal (Visual Comparison):

      - Displays old_value vs new_value in split-pane or highlighted JSON diff, showing exact price or quantity alterations.

  - Export audit log to CSV/Excel format.

- Deliverables: Complete administrative governance console for auditing staff actions.

- Acceptance Criteria: Every modification in products, sales, cash sessions, and discounts is inspectable with old vs new values.

### Sub-Task BE-4.4: Business Intelligence Reports & Automated Cron Jobs

- Domain: Backend Jobs & Frontend Reporting Dashboard

- Time Estimate: 8 Hours (Sep 30, 04:30 PM – 10:30 PM)

- Dependencies: All sales and inventory data operational.

- Detailed Execution Steps:

  - Financial & Stock Reporting APIs:

    - Daily/Monthly sales revenue and net profit calculator.

    - Fast-moving vs Dead inventory report.

    - Low Stock Alert report (items below reorder_point).

  - Reports Dashboard UI in client-swm/:

    - Interactive charts (Recharts/Chart.js) for revenue trends and top-selling variants.

    - Export to PDF and Excel buttons.

  - Automated Cron Jobs (Scheduled via BullMQ / Node-Cron):

    - Daily Database Backup Job (03:00 AM): Executes mysqldump, compresses into .sql.gz, encrypts with AES-256, and stores in /var/backups/yoka/.

    - Cart Abandonment Cleanup (Every 5 minutes): Releases expired reservations.

    - Low Stock Email Digest (Daily 09:00 AM): Sends summary to store manager.

- Deliverables: Executive reports dashboard and production background automation scripts.

- Hand-off Checklist to Entire Team:

  - Activity Log Viewer displays all historic events with visual diffs.

  - Reports dashboard calculates accurate revenue, costs, and inventory values.

  - Automated cron jobs tested and running via PM2.

  - System ready for final day joint stress testing and live production release.

# 6. Joint Final Day: All 4 Members (Day 7 — October 01, 2026)

## Objective: End-to-End Stress Testing, Concurrency Verification, Production Deployment & Official Go-Live

Window: Oct 01, 2026 (08:00 AM) to Oct 01, 2026 (08:00 PM)
Lead Coordinator: Moustafa Maher
Participants: Moustafa Maher, Yassen Ahmed, Adel Ahmed, Boda Essam

## Hour-by-Hour Execution Plan:

| Time Slot | Primary Activity | Lead Member | Support Members | Verification Target |
| --- | --- | --- | --- | --- |
| 08:00 AM – 11:30 AM | Concurrency & Race Condition Simulation | Moustafa Maher | Yassen, Adel | Simulate 5 cashiers selling last items while online shoppers checkout. |
| 11:30 AM – 01:00 PM | Load Testing (Autocannon / K6) | Yassen Ahmed | Boda | Confirm average response latency < 120ms at 200 req/sec. |
| 01:30 PM – 03:30 PM | Staging Sanitization & Initial Seed | Boda Essam | Adel | Flush mock data; seed real branches, staff, and physical stock. |
| 03:30 PM – 06:30 PM | Production Deployment & Domain Linking | Moustafa Maher | All | Official DNS, Wildcard SSL, PM2 Cluster & Nginx tuning. |
| 06:30 PM – 08:00 PM | Final Smoke Test & Executive Handover | All Members | All | 1 live POS sale and 1 E-Commerce order with real payment. |

# 7. Member-by-Member Daily Responsibility Matrix

| Date | Moustafa Maher | Yassen Ahmed | Adel Ahmed | Boda Essam |
| --- | --- | --- | --- | --- |
| Sep 25 | ACTIVE (Bulk 1): VPS setup, MySQL & Redis tuning, 35+ DB tables | Code review of DB schema; local environment prep | Reviewing ECP UI wireframes and Tailwind setup | Reviewing reporting metrics and Log requirements |
| Sep 26 | ACTIVE (Bulk 1): Finish Master Data APIs, Auth JWT & UI | ACTIVE (Bulk 2): Takes hand-off; builds Supplier & Purchase APIs | Preparing Next.js store structure and fetch clients | Preparing customer portal and review schema |
| Sep 27 | Code review on Bulk 2 PR; DB query indexing validation | ACTIVE (Bulk 2): Builds POS UI & Thermal Print | Testing POS sales data and cart integration hooks | Preparing coupon rules and WhatsApp logic |
| Sep 28 | Infrastructure monitoring and Redis pool checks | Assisting Adel with inventory reservation queries | ACTIVE (Bulk 3): Builds Catalog, PDP & Cart | Building Activity Log Explorer UI component |
| Sep 29 | Database query analysis on high-frequency queries | Supporting checkout Webhooks verification | ACTIVE (Bulk 3): Finishes Checkout & Payment | ACTIVE (Bulk 4): Portal & WhatsApp notifications |
| Sep 30 | Security vulnerability scan and audit validation | Verifying Cron scripts and Redis memory usage | Assisting Boda with report chart integration | ACTIVE (Bulk 4): Log UI, Reports & Backup |
| Oct 01 | LEAD (Day 7): Race condition test lead, SSL, Go-Live | Load testing lead, webhook verification, payment audit | Frontend smoke test lead, mobile audit | Real-data seeding verification, live demo |

# 8. Activity Log Implementation Standard (Mandatory for ALL Members)

Every member writing any mutation endpoint (POST, PUT, DELETE, PATCH) must include the following standard snippet:const { logActivity } = require('../shared/activityLogger');

// Inside your controller method:

await logActivity({

userId: req.user.id,

branchId: req.user.branchId || targetBranchId,

actionType: 'UPDATE_PRODUCT_PRICE', // or 'POS_SALE', 'PURCHASE_RECEIVE', 'CASH_WITHDRAWAL'

entityType: 'product_variants',

entityId: variantId,

oldValue: { price: previousPrice, cost: previousCost },

newValue: { price: updatedPrice, cost: updatedCost },

ipAddress: req.ip,

userAgent: req.headers['user-agent'],

notes: 'Price adjustment by store manager'

});

[!IMPORTANT]
Quality Gate: A Pull Request will be rejected immediately if any state-changing function lacks logActivity() or fails to use atomic db.beginTransaction() for monetary and stock movements.